# SMARTGRID-X Project Plan

Sep 29, 2026 · @Rajwardhan Shinde

We measure how much electricity a real Indian campus wastes when buildings are nearly empty, and build a system that flags it automatically.

## Project at a glance

SMARTGRID-X: occupancy-aware energy analysis of a real Indian campus. We combine 4 years of electricity readings with WiFi-based occupancy counts for 7 buildings at IIIT Delhi to find energy used when nobody is there.

Every chart, model and finding in the project must answer one of these three questions:

- Main question: how much of each building's energy is used when occupancy is near zero?

- How well do occupancy and time of day predict a building's power use?

- Can we flag abnormal usage automatically, and how accurately?

If a piece of work does not serve one of these, we cut it.

## Dataset

We use I-BLEND, a public dataset from IIIT Delhi (paper, data). Both parts are downloaded and in the Dataset folder.

| Part | Files | Columns | Resolution | Period |
| --- | --- | --- | --- | --- |
| Energy | 9 building meters + 3 transformers + 2 combined files (~1.6 GB) | timestamp, power (W), current, voltage, frequency, power_factor | 1 minute | Aug 2013 – Dec 2017 |
| Occupancy | 7 CSVs, one per building (~21 MB) | timestamp, occupancy_count | 10 minutes | Feb 2014 – Nov 2017 |
| Data status | 2 CSVs | 1 = reading present, 0 = missing, per building per minute | 1 minute | same as energy |

Buildings: Academic, Boys' Hostel, Girls' Hostel, Dining (Mess), Library, Lecture, Facilities. The hostels have separate mains and UPS meters.

Start with all_buildings_power.csv: it has every building's power side by side in one file.

Known data problems (these become our cleaning work):

- current is empty (NA) in the early rows of most files

- power_factor is sometimes negative, which is not physically valid

- The Lecture building shows 0 power for long stretches, which suggests a dead meter

- The Facilities and Mess meters start months later than the others

- Timestamps are UNIX format and must be converted to Asia/Kolkata time

- Energy is per minute and occupancy is per 10 minutes, so energy must be averaged into 10-minute blocks before merging

Not in the dataset: weather, floor area, reactive power, equipment IDs. We do not use or claim any of these.

## Final output

We submit three things, all in Python.

| Deliverable | What it contains | Who it's for |
| --- | --- | --- |
| Report | Problem, data, method, findings with charts, limitations, future scope | Examiner (this is what is graded) |
| Jupyter notebook | The full pipeline, one section per phase below, runs top to bottom | Examiner and teacher, to verify the work |
| Streamlit dashboard | One page: pick a building, see power vs. occupancy, flagged anomalies and its wasted-energy % | Live demo during the presentation |

The headline result we are working toward is one sentence per building, for example: "The Library uses X% of its electricity when fewer than 5 people are inside."

## Plan of action

Phase 0 comes first: a rough version of the whole pipeline on one building (Academic), so we can always show a working project. Phases 1–7 then extend and improve it.

| Phase | Work | What it produces | Syllabus |
| --- | --- | --- | --- |
| 0. Rough pipeline | Academic building only: load, merge, basic cleaning, a few charts, simple regression, basic anomaly flags | A working end-to-end demo | All units, lightly |
| 1. Data prep | Convert timestamps, average energy to 10-min blocks, merge with occupancy, handle NAs, negative power factor, dead meters, missing periods | One clean merged table per building + a data quality summary | Unit III, IV, V |
| 2. Understand | Classify attribute types; mean, median, mode, spread, IQR; histograms and box plots; hourly, weekly and seasonal patterns; hostel vs. academic comparison | EDA charts and a statistics table | Unit II, V, VI |
| 3. PCA | Turn each day into a 24-hour load vector, run PCA, group similar days (weekday, weekend, vacation) | Scree plot + 2D day-type chart | Unit IV |
| 4. Regression | Linear, then multiple linear regression: power ~ occupancy + hour + day of week + month. Train-test split, MAE, RMSE, R² | Model results and an actual vs. predicted chart | Unit I, V, VI |
| 5. Anomaly detection | Residual = actual − predicted power; flag with IQR and Z-score as NORMAL / WARNING / ANOMALY. Inject a small set of labelled fake anomalies to compute a confusion matrix, precision and recall | Flagged anomalies + evaluation scores | Unit III, V |
| 6. Wasted-energy analysis | Energy used when occupancy is near zero, per building, as a % of total | The headline finding | Unit II, VI |
| 7. Deliver | Streamlit dashboard, report, presentation | Final submission | Unit VI |

The injected anomalies in phase 5 are for testing only. The report must say clearly that they are synthetic and never present them as real faults.

## Novelty

The methods are standard; the novelty is in the question and in combining the two datasets.

- Energy + occupancy together. Most work on energy data looks at power alone. We model power against how many people are actually in the building.

- Occupancy-aware anomaly detection. A reading is abnormal when it is far from what the building's occupancy predicts, not when it crosses a fixed threshold.

- A concrete, measurable answer. The output is a wasted-energy % per building on a real Indian campus, not a generic forecast.

If asked "what's new here?", the one-line answer is: we measure energy used by empty buildings, and detect it automatically.

## Team roles

Fill in names. Everyone helps with Phase 0.

| Role | Owns | Name |
| --- | --- | --- |
| Data lead | Phase 1: loading, merging, cleaning, data quality summary |  |
| Analysis lead | Phases 2–3: statistics, EDA, PCA |  |
| Modelling lead | Phases 4–5: regression, anomaly detection, evaluation |  |
| Insight lead | Phase 6: wasted-energy analysis and headline findings |  |
| Delivery lead | Phase 7: dashboard, report, slides |  |

## How we work

The teacher can ask to see progress at any time, so the project must always be in a showable state.

- ☐ One notebook that always runs top to bottom. Never leave it broken overnight.

- ☐ Shared GitHub repo. Everyone commits their own work, so progress and contributions are visible.

- ☐ progress.md in the repo. Three lines per update: what was done, what we found, what's next.

- ☐ Load one building at a time. 1.6 GB of 1-minute data is slow in pandas; average it into 10-minute blocks first and save the result.

- ☐ Never invent numbers. Every figure in the report comes from the notebook.

## Out of scope

These were in the original project description but are dropped. They go in the report as one line each under Future scope.

- Weather integration and floor-area energy intensity (not in the dataset)

- Fault intelligence, Energy Health Index, recommendation engine

- Gradient boosting and other advanced models

- Real-time IoT, streaming, cloud, API or production architecture